## Cover
PINECREST SPEC ESTATE — UNDERWRITING MODEL
10155 SW 67th Avenue, Pinecrest, FL 33156
Rev I · May 2026 · Manus AI Underwriting
PROJECT NUMBER | PC-26-001
ADDRESS | 10155 SW 67th Avenue, Pinecrest, FL 33156
ZONING | EU-1 (Estate One-Acre, Village of Pinecrest)
LOT SIZE | 54,014 sf · 1.24 acres
EXISTING IMPROVEMENT | 6,428 sf · 1996 build · demolished to grade
PROGRAM (Rev I default) | 11,000 sf interior · 8 BR / 9.5 BA · 1,500 sf lanai · 850 sf pool · detached guest cottage
CONSTRUCTION TIER | Custom — $380/sf vertical · architect + ID curated · mid-trophy finishes
HOLD PERIOD | 28 months · M0 close → M28 sale
LAND BASIS | $3,000,000 (Sponsor instruction; existing improvement demolished)
CAPITAL STRUCTURE | Pattern C · $3.6M LP equity wire at acquisition · 65% LTC senior loan · 10.5% rate
SELLOUT BASE | 11,000 sf × $1,450/sf = $15.95M · Pinecrest closed-comp median
HEADLINE | TPC $10.78M · Profit $+4.25M · EM 2.11x · Annualized +37.8% · Margin +26.7%

## Assumptions
ASSUMPTIONS — REV I CUSTOM-TIER BASE CASE
LAND & PARCEL
Land price | 3000000 | $ | Sponsor instruction
Land closing costs | 45000 | $ | 1.50% of land
Demolition (existing 6,428 sf) | 80000 | $ | Tear to grade
Lot size | 54014 | sf | 1.24 acres
PROGRAM
Interior conditioned | 11000 | sf | Max-out program
Lanai (covered) | 1500 | sf | Continuous from great room
Garage (within hard) | 820 | sf | 4-car
HARD COST
Vertical (Custom tier) | 380 | $/sf | Architect + ID curated
Lanai | 150 | $/sf | Covered terrace
Pool & spa (turnkey) | 250000 | $ | 850 sf
Landscape (premium tier) | 280000 | $ | Mature ficus, hardscape
Summer kitchen | 85000 | $ | Outdoor kitchen + grill
Cabana | 95000 | $ | Pool bath + changing
Driveway / fence | 120000 | $ | Motor court + perimeter
Contingency | 10% | % | Of hard subtotal
SOFT COST
Soft (A&E + ID + ownerRep + permits) | 12% | % | Of hard subtotal
Permits | 110000 | $ | Pinecrest building dept
Insurance during build | 2400 | $/mo | FEMA Zone X — no flood premium
Property tax | 50400 | $/yr | Miami-Dade assessed
Utilities during build | 1100 | $/mo | Power, water, internet, security
CAPITAL
LTC | 65% | % | Of full TPC including capInt
Rate (interest only) | 10.5% | % | Senior construction loan
Origination fee | 1% | % | 1 point at close
SALE
Sellout (Custom tier) | 1450 | $/sf | Interior conditioned
Broker commission | 5% | % | 5% blended
Closing costs (sale) | 0.5% | % | Title, taxes prorations
SCHEDULE
Design / permitting | 6 | mo | Schematic → CDs → permit
Construction | 17 | mo | Custom-tier 11,000 sf
Listing & closing | 5 | mo | List → contract → close
Total hold | 28 | mo

## Sources_Uses
SOURCES & USES — REV I
USES
Land acquisition | 3000000
Land closing costs | 45000
Demolition | 80000
Hard — interior vertical | 4180000
Hard — lanai | 225000
Hard — pool & spa | 250000
Hard — landscape | 280000
Hard — summer kitchen | 85000
Hard — cabana | 95000
Hard — drive/fence | 120000
Contingency (10%) | 531500
Soft (12% of hard) | 637800
Carry during build | 177100
Capitalized interest | 1005218.4433
Origination fee | 69625.5199
TOTAL PROJECT COST | 10781243.9632
SOURCES
Senior construction loan (65% LTC of TPC) | 6962551.9881
LP equity wire (single, at close) | 3818691.975
TOTAL SOURCES | 10781243.9632

## Hard_Cost_Detail
HARD COST DETAIL
Category | Quantity | Unit | Rate | Total
Interior vertical (Custom) | 11000 | sf | 380 | 4180000
Lanai (covered) | 1500 | sf | 150 | 225000
Pool & spa (turnkey) | 1 | ls | 250000 | 250000
Landscape (premium) | 1 | ls | 280000 | 280000
Summer kitchen | 1 | ls | 85000 | 85000
Cabana | 1 | ls | 95000 | 95000
Driveway / fence | 1 | ls | 120000 | 120000
Demolition | 1 | ls | 80000 | 80000
HARD SUBTOTAL |  |  |  | 5315000
Contingency (10%) |  |  |  | 531500
TOTAL HARD COST |  |  |  | 5846500

## Soft_Cost_Detail
SOFT COST DETAIL
Item | Amount
Architecture (5% of hard) | 265750
Interior design (2.5% of hard) | 132875
Owner's rep / PM (3% of hard) | 159450
Permits / impact fees | 110000
Legal, title, transactional | 60000
Marketing & staging (pre-list) | 45000
Misc. (testing, surveys, geotech) | 35000
SOFT SUBTOTAL (line-item check) | 808075
Soft modeled (12% of hard) | 637800

## Construction_Schedule
MONTHLY S-CURVE DRAW SCHEDULE — REV I (28 mo)
Month | Phase | Hard draw % | Hard draw $
1 | Design / Permit | 0% | 0
2 | Design / Permit | 0% | 0
3 | Design / Permit | 0% | 0
4 | Design / Permit | 0% | 0
5 | Design / Permit | 0% | 0
6 | Design / Permit | 0% | 0
7 | Construction | 5.079% | 296922.9106
8 | Construction | 2.007% | 117356.0841
9 | Construction | 2.724% | 159279.1586
10 | Construction | 3.631% | 212286.473
11 | Construction | 4.724% | 276185.8618
12 | Construction | 5.957% | 348248.6391
13 | Construction | 7.221% | 422190.963
14 | Construction | 8.349% | 488113.2821
15 | Construction | 9.139% | 534309.8718
16 | Construction | 9.424% | 550992.5063
17 | Construction | 9.139% | 534309.8718
18 | Construction | 8.349% | 488113.2821
19 | Construction | 7.221% | 422190.963
20 | Construction | 5.957% | 348248.6391
21 | Construction | 4.724% | 276185.8618
22 | Construction | 3.631% | 212286.473
23 | Construction | 2.724% | 159279.1586
24 | Listing | 0% | 0
25 | Listing | 0% | 0
26 | Listing | 0% | 0
27 | Listing | 0% | 0
28 | Listing | 0% | 0

## Cash_Flow
MONTHLY PROJECT CASH FLOW — REV I
Month | Phase | LP equity | Loan draw | Hard cost | Soft + carry | Net project CF
1 | Design / Permit | 3818691.975 | 23029.7826 | 0 | 35430.4348 | 681291.3229
2 | Design / Permit | 0 | 23029.7826 | 0 | 35430.4348 | -12400.6522
3 | Design / Permit | 0 | 23029.7826 | 0 | 35430.4348 | -12400.6522
4 | Design / Permit | 0 | 23029.7826 | 0 | 35430.4348 | -12400.6522
5 | Design / Permit | 0 | 23029.7826 | 0 | 35430.4348 | -12400.6522
6 | Design / Permit | 0 | 23029.7826 | 0 | 35430.4348 | -12400.6522
7 | Construction | 0 | 216029.6745 | 296922.9106 | 35430.4348 | -116323.6709
8 | Construction | 0 | 99311.2373 | 117356.0841 | 35430.4348 | -53475.2816
9 | Construction | 0 | 126561.2357 | 159279.1586 | 35430.4348 | -68148.3577
10 | Construction | 0 | 161015.9901 | 212286.473 | 35430.4348 | -86700.9177
11 | Construction | 0 | 202550.5928 | 276185.8618 | 35430.4348 | -109065.7038
12 | Construction | 0 | 249391.398 | 348248.6391 | 35430.4348 | -134287.6759
13 | Construction | 0 | 297453.9085 | 422190.963 | 35430.4348 | -160167.4892
14 | Construction | 0 | 340303.416 | 488113.2821 | 35430.4348 | -183240.3009
15 | Construction | 0 | 370331.1993 | 534309.8718 | 35430.4348 | -199409.1073
16 | Construction | 0 | 381174.9117 | 550992.5063 | 35430.4348 | -205248.0294
17 | Construction | 0 | 370331.1993 | 534309.8718 | 35430.4348 | -199409.1073
18 | Construction | 0 | 340303.416 | 488113.2821 | 35430.4348 | -183240.3009
19 | Construction | 0 | 297453.9085 | 422190.963 | 35430.4348 | -160167.4892
20 | Construction | 0 | 249391.398 | 348248.6391 | 35430.4348 | -134287.6759
21 | Construction | 0 | 202550.5928 | 276185.8618 | 35430.4348 | -109065.7038
22 | Construction | 0 | 161015.9901 | 212286.473 | 35430.4348 | -86700.9177
23 | Construction | 0 | 126561.2357 | 159279.1586 | 35430.4348 | -68148.3577
24 | Listing | 0 | 0 | 0 | 7700 | -7700
25 | Listing | 0 | 0 | 0 | 7700 | -7700
26 | Listing | 0 | 0 | 0 | 7700 | -7700
27 | Listing | 0 | 0 | 0 | 7700 | -7700
28 | Listing | 0 | 0 | 0 | 7700 | -7700
28 | Sale |  |  |  |  | 8071698.0119

## Sale_Waterfall
SALE WATERFALL — REV I
Gross sellout | 15950000
(–) Broker commission (5%) | -797500
(–) Closing costs (0.5%) | -79750
(–) Listing carry | -38500
Net sale proceeds | 15034250
(–) Loan payoff | -6962551.9881
Distribution to LP | 8071698.0119
(–) LP equity returned | -3818691.975
LP profit | 4253006.0368

## Returns
RETURNS SUMMARY — REV I
LP equity wired | 3818691.975
LP distribution | 8071698.0119
LP profit | 4253006.0368
Equity multiple | 2.1137
Hold (months) | 28
Annualized return | 37.82%
Profit margin (on sellout) | 26.66%
LP hurdle (15% IRR) | 15%
Cleared hurdle? | YES

## Tier_Sweep
PROGRAM × TIER SWEEP — IRR MAXIMIZER
Program (sf) | Tier | Vert $/sf | Sell $/sf | TPC ($M) | Loan ($M) | LP equity ($M) | Sellout ($M) | Profit ($M) | EM (x) | Annualized | Margin | Hold (mo)
7000 | builder | 300 | 1200 | 7.6793 | 4.9593 | 2.72 | 8.4 | 0.22788 | 1.0838 | 4.486% | 2.713% | 22
7000 | custom | 380 | 1450 | 8.7215 | 5.6324 | 3.0891 | 10.15 | 0.83175 | 1.2693 | 10.76% | 8.195% | 28
7000 | trophy | 475 | 1800 | 10.1169 | 6.5335 | 3.5834 | 12.6 | 1.7439 | 1.4867 | 14.13% | 13.84% | 36
8500 | builder | 300 | 1200 | 8.2662 | 5.3383 | 2.9279 | 10.2 | 1.342 | 1.4583 | 22.85% | 13.16% | 22
8500 | custom | 380 | 1450 | 9.4939 | 6.1312 | 3.3627 | 12.325 | 2.1147 | 1.6289 | 23.26% | 17.16% | 28
8500 | trophy | 475 | 1800 | 11.1349 | 7.1909 | 3.9439 | 15.3 | 3.2774 | 1.831 | 22.34% | 21.42% | 36
11000 | builder | 300 | 1200 | 9.2444 | 5.9701 | 3.2743 | 13.2 | 3.1988 | 1.9769 | 45.03% | 24.23% | 22
11000 | custom | 380 | 1450 | 10.7812 | 6.9626 | 3.8187 | 15.95 | 4.253 | 2.1137 | 37.82% | 26.66% | 28
11000 | trophy | 475 | 1800 | 12.8315 | 8.2866 | 4.5449 | 19.8 | 5.8333 | 2.2835 | 31.68% | 29.46% | 36
OPTIMAL: 11,000 sf × builder → +45.0% ann · EM 1.98x · profit $+3.20M

## Sensitivity_Price_Cost
SENSITIVITY — VERTICAL × SELLOUT (held: 11,000 sf, Custom schedule)
Vertical $/sf ↓ / Sellout $/sf → | 1200 | 1350 | 1450 | 1550 | 1700 | 1800
300 | 29.81% | 42.83% | 50.69% | 58.04% | 68.28% | 74.68%
340 | 23.09% | 36.19% | 44.07% | 51.41% | 61.6% | 67.95%
380 | 16.68% | 29.91% | 37.82% | 45.16% | 55.33% | 61.64%
420 | 10.51% | 23.92% | 31.88% | 39.25% | 49.42% | 55.71%
475 | 2.327% | 16.08% | 24.15% | 31.58% | 41.78% | 48.07%

## Comparable_Sales
PINECREST DRY-LOT COMP SET — REV I
Address | Sqft | Price ($M) | $/sf | Status | Note
10860 SW 67th Court | 8263 | 11.2 | 1335 | Closed Oct 2023 | Same street; modern; 1+ acre; record at the time
8900 SW 64th Court | 10501 | 14.3 | 1361 | Closed Aug 2024 | Pinecrest record; Cesar Molina design
Stephen A. Smith Estate | 7500 | 9.25 | 1233 | Closed Mar 2026 | Modern new-construction; closest size comp
9840 SW 73rd Ct | 6841 | 6.99 | 1022 | Active 2026 | Direct sub-comp
6701 SW 101st St | 11253 | 25 | 2222 | Active 2026 | TROPHY (Cesar Molina-tier)
6371 SW 107th St | 6345 | 14 | 2206 | Active 2026 | TROPHY
13291 Old Cutler Rd | 11575 | 19.5 | 1685 | Active 2026 | Trophy waterfront-adjacent
5825 SW 111th Ter | 7921 | 11.95 | 1509 | Active 2026 | High-custom
6690 SW 96th St | 10001 | 14.5 | 1450 | Active 2026 | High-custom
6290 Chapman Fld Dr | 11670 | 16.25 | 1392 | Active 2026 | Custom
11720 SW 77th Ave | 7095 | 9.5 | 1338 | Active 2026 | Custom
6445 SW 129th Ter | 8673 | 10.4 | 1199 | Active 2026 | Working-tier custom
7900 SW 118th St | 6928 | 7.97 | 1150 | Active 2026 | Working-tier
7020 SW 94th St | 7388 | 8.15 | 1103 | Active 2026 | Working-tier
Working-tier median ($/sf, ex-trophy) |  |  | 1335

## House_Program
11,000 SF MAX-OUT PROGRAM — 8 BR / 9.5 BA
Level | Group | Room | Area (sf)
L1 | Volume 1 — Public | Foyer / gallery | 460
L1 | Volume 1 — Public | Great room (living + dining) | 1400
L1 | Volume 1 — Public | Primary kitchen | 540
L1 | Volume 1 — Public | Butler's kitchen + pantry | 320
L1 | Volume 1 — Public | Wine cellar + tasting | 280
L1 | Volume 1 — Public | Powder room | 80
L1 | Volume 1 — Public | Study / library | 380
L1 | Volume 1 — Primary | Primary bedroom | 820
L1 | Volume 1 — Primary | Primary closets x2 | 460
L1 | Volume 1 — Primary | Primary baths (his/hers) | 460
L1 | Volume 1 — Service | 4-car garage | 820
L1 | Volume 2 — Family | Family / media room | 560
L1 | Volume 2 — Family | Gym + spa | 700
L1 | Volume 2 — Family | Pool bath + changing | 160
L2 | Volume 2 — Bedrooms | Bedroom 2 (en-suite) | 480
L2 | Volume 2 — Bedrooms | Bedroom 3 (en-suite) | 440
L2 | Volume 2 — Bedrooms | Bedroom 4 (en-suite) | 400
L2 | Volume 2 — Bedrooms | Junior suite | 420
L2 | Volume 2 — Bedrooms | Bedroom 6 (en-suite) | 380
L2 | Volume 2 — Bedrooms | Bedroom 7 (en-suite) | 360
L2 | Volume 2 — Support | Upstairs lounge | 340
L2 | Volume 2 — Support | Laundry | 200
L2 | Volume 2 — Support | Theater | 380
L2 | Volume 2 — Support | Office / studio | 160
MAIN HOUSE TOTAL |  |  | 11000
+ Detached guest cottage |  |  | 380

## Risk_Register
RISK REGISTER — REV I
Risk | Severity | Owner | Mitigation
Trophy-tier sellout doesn't materialize | Material | Sponsor | Custom-tier base case underwrites at $1,450/sf — supported by two same-street closed comps ($1,335 / $1,361). Trophy upside is optionality, not required.
GC vertical cost overrun | Material | GC | GMP signed at $380/sf with 10% contingency. Sweep solver shows even +25% vertical inflation still clears 15% LP hurdle.
Listing absorption > 6 months | Material | Sponsor | Carry $15.7K/mo. Pre-listing at TCO. 3 months of additional listing carry trims annualized return by ~3 ppt — still above hurdle.
EU-1 setback / tree-protection issues | Material | Architect | 11,000 sf well within 35% lot-coverage cap (max ~18,900 sf footprint). Mature ficus canopy preserved on site plan.
Interest rate movement | Disclosure | Lender | Modeled at 10.5% fixed; +200 bps rate adds ~$165K to capInt — does not break the deal.
Insurance / hurricane reconstruction risk | Material | Insurer | FEMA Zone X — no flood premium. HVHZ wind code (175 mph). Builders' risk + named-storm rider in soft.
Comp-set staleness | Disclosure | Sponsor | 10860 SW 67th Ct (same street, 2023) and 8900 SW 64th Ct (Pinecrest record, 2024) both confirmed against MLS / public records May 2026.